Polar Senior Review Development Schedule:

May 6: Polar PI telecon

May 6-May 13: Skeleton Draft

May 13-20: writing assignments, formation of Red Team

May 23-27: AGU meeting in New Orleans (can we get together)

June 1-24: Draft 1 (circulated 20th), Polar PI Telecon 24th)

June 27-July 1: Draft 1 to red team for concept/structure review??

June 27-July 1: GEM meeting in Santa Fe (can we get together)

July 5-11: Draft 2 (circulated 11th, Polar PI Telecon 14th)

July 15-August 5: Draft 3 (circulated August 1st, Polar PI Telecon 5th)

July18-29: IAGA meeting in Toulouse, France

August 6-14: Draft 4

August 15: Draft 4 sent to Red Team

August 22-23: Red Team Review

August 25: Polar PI Telecon

August 26-September 5: Draft 5 (circulated 5th)

September 12-19: Draft 6 to PI team for last review/editing, Polar telecon (16th)

September 20-26: final formatting, proofing

September 27-30: Printing and delivery